## Dashboard
Digital Banking Request Dashboard
As-of date used | 2026-10-26 |  | Fictional data for portfolio purposes. All figures calculate from the Request Tracker sheet.
Override date (optional)
Total Requests | Open Requests | Overdue | Due Soon | High Priority Open | SLA Compliance | Avg Turnaround (days) | Completion Rate
40 | 25 | 4 | 7 | 10 | 73.33% | 6 | 37.5%
1. Requests by Priority and Status
Priority | Pending | In Progress | Completed | Total | Overdue
High | 6 | 4 | 5 | 15 | 2
Medium | 4 | 5 | 8 | 17 | 0
Low | 3 | 3 | 2 | 8 | 2
Total | 13 | 12 | 15 | 40 | 4
2. Performance by Department
Department | Total | Open | Overdue | SLA Met % | Avg Turnaround (days)
IT | 7 | 3 | 1 | 100% | 5
Operations | 6 | 4 | 1 | 100% | 3.5
Digital Banking | 7 | 4 | 0 | 66.67% | 4.6667
Compliance | 4 | 2 | 0 | 100% | 6.5
Customer Support | 5 | 4 | 0 | 0% | 3
Risk | 4 | 3 | 1 | 100% | 7
Marketing | 3 | 2 | 1 | 0% | 13
Finance | 4 | 3 | 0 | 0% | 13
Total | 40 | 25 | 4 | 73.33% | 6
3. Assignee Workload vs Capacity
Assignee | Department | Open | Overdue | Capacity | Utilization
Ayesha Khan | Digital Banking | 3 | 0 | 8 | 37.5%
Hamza Malik | IT | 4 | 1 | 8 | 50%
Sana Raza | Operations | 4 | 1 | 7 | 57.14%
Bilal Ahmed | Compliance | 3 | 0 | 6 | 50%
Fatima Noor | Customer Support | 3 | 0 | 7 | 42.86%
Usman Tariq | Risk | 2 | 1 | 5 | 40%
Zainab Ali | Finance | 2 | 0 | 6 | 33.33%
Omar Siddiqui | Digital Banking | 4 | 1 | 8 | 50%
4. Aging of Open Requests
Age Bucket | Open Requests
0 to 3 days | 9
4 to 7 days | 12
8 to 14 days | 3
15+ days | 1
Total | 25 | Matches open
5. Top 5 Requests at Risk (open, ranked by risk score)
Request | Department | Assigned To | Deadline | Flag | Risk Score | Row #
DB-006 - Password reset flow fix | IT | Hamza Malik | 2026-10-24 | OVERDUE | 9 | 6
DB-009 - Fraud alert threshold review | Risk | Usman Tariq | 2026-10-22 | OVERDUE | 9 | 9
DB-004 - KYC process review | Compliance | Bilal Ahmed | 2026-10-27 | Due Soon | 6 | 4
DB-018 - Biometric login rollout checklist | Digital Banking | Ayesha Khan | 2026-10-28 | Due Soon | 6 | 18
DB-020 - Digital channel fee reconciliation | Finance | Zainab Ali | 2026-10-26 | Due Soon | 6 | 20
6. Data Quality Checks
Check | Rows Flagged
Missing completion date | 0
Completion date on open request | 0
Deadline before raised | 0
Overall | All clear
Formulas:
Due Soon = IF([Avg Turnaround (days)]="","",INDEX('Request Tracker'!$I6:I65,[Avg Turnaround (days)]))
Note on C4: Leave blank to use today's date. Type a date (e.g. 30-Oct-2026) to test overdue and SLA logic.

## Request Tracker
Digital Banking Team Request Tracker
Fictional data for portfolio purposes.
Edit only the yellow-shaded columns A to J. Columns K to T calculate automatically (column S is a hidden sort helper).
As-of date: | 2026-10-26
Request ID | Date Raised | Department | Request Type | Request | Priority | Status | Assigned To | Deadline | Completed On | SLA (days) | SLA Target | Days Left | Turnaround (days) | Age (days) | Flag | SLA Status | Risk Score | Sort Key | Data Check
DB-001 | 2026-10-23 | IT | Access Request | Access request | High | Pending | Hamza Malik | 2026-10-30 |  | 2 | 2026-10-27 | 4 |  | 3 | On Track | Within SLA | 3 | 3.0099 | OK
DB-002 | 2026-10-21 | Operations | Report | Report preparation | Medium | In Progress | Sana Raza | 2026-10-31 |  | 5 | 2026-10-28 | 5 |  | 5 | On Track | Within SLA | 2 | 2.0099 | OK
DB-003 | 2026-10-22 | Digital Banking | Testing Support | Testing support | High | Completed | Ayesha Khan | 2026-10-28 | 2026-10-23 | 2 | 2026-10-26 |  | 1 |  | Done | Met | 0 | 0.00992 | OK
DB-004 | 2026-10-22 | Compliance | Compliance Review | KYC process review | High | In Progress | Bilal Ahmed | 2026-10-27 |  | 2 | 2026-10-26 | 1 |  | 4 | Due Soon | Within SLA | 6 | 6.0099 | OK
DB-005 | 2026-10-26 | Customer Support | Documentation | Mobile app FAQ update | Low | Pending | Fatima Noor | 2026-11-04 |  | 8 | 2026-11-05 | 9 |  | 0 | On Track | Within SLA | 1 | 1.0099 | OK
DB-006 | 2026-10-19 | IT | Incident Fix | Password reset flow fix | High | Pending | Hamza Malik | 2026-10-24 |  | 2 | 2026-10-21 | -2 |  | 7 | OVERDUE | Breached | 9 | 9.0099 | OK
DB-007 | 2026-10-16 | Operations | Report | Daily transaction summary | Medium | Completed | Sana Raza | 2026-10-23 | 2026-10-22 | 5 | 2026-10-23 |  | 6 |  | Done | Met | 0 | 0.00988 | OK
DB-008 | 2026-10-20 | Digital Banking | Testing Support | UAT test case documentation | Medium | In Progress | Omar Siddiqui | 2026-10-29 |  | 5 | 2026-10-27 | 3 |  | 6 | On Track | Within SLA | 2 | 2.0099 | OK
DB-009 | 2026-10-15 | Risk | Compliance Review | Fraud alert threshold review | High | Pending | Usman Tariq | 2026-10-22 |  | 2 | 2026-10-19 | -4 |  | 11 | OVERDUE | Breached | 9 | 9.0099 | OK
DB-010 | 2026-10-19 | Marketing | Documentation | Mobile banking launch banner copy | Low | In Progress | Fatima Noor | 2026-11-06 |  | 8 | 2026-10-29 | 11 |  | 7 | On Track | Within SLA | 1 | 1.0098 | OK
DB-011 | 2026-10-23 | Finance | Report | Monthly fee income report | Medium | Pending | Zainab Ali | 2026-11-02 |  | 5 | 2026-10-30 | 7 |  | 3 | On Track | Within SLA | 2 | 2.0098 | OK
DB-012 | 2026-10-19 | IT | Access Request | API access for payments team | Medium | Completed | Hamza Malik | 2026-10-26 | 2026-10-26 | 5 | 2026-10-26 |  | 7 |  | Done | Met | 0 | 0.00983 | OK
DB-013 | 2026-10-26 | Customer Support | Report | Complaint log analysis | Low | Pending | Fatima Noor | 2026-11-09 |  | 8 | 2026-11-05 | 14 |  | 0 | On Track | Within SLA | 1 | 1.0098 | OK
DB-014 | 2026-10-12 | Digital Banking | Documentation | Internet banking user guide | Medium | Completed | Ayesha Khan | 2026-10-21 | 2026-10-23 | 5 | 2026-10-19 |  | 11 |  | Done (Late) | Missed | 0 | 0.00981 | OK
DB-015 | 2026-10-22 | Compliance | Compliance Review | Audit evidence collection | High | In Progress | Bilal Ahmed | 2026-11-03 |  | 2 | 2026-10-26 | 8 |  | 4 | On Track | Within SLA | 3 | 3.0098 | OK
DB-016 | 2026-10-20 | IT | Change Request | Add OTP timeout parameter | Medium | In Progress | Hamza Malik | 2026-10-30 |  | 5 | 2026-10-27 | 4 |  | 6 | On Track | Within SLA | 2 | 2.0098 | OK
DB-017 | 2026-10-14 | Operations | Incident Fix | Failed fund transfer reconciliation | High | Completed | Sana Raza | 2026-10-16 | 2026-10-15 | 2 | 2026-10-16 |  | 1 |  | Done | Met | 0 | 0.00978 | OK
DB-018 | 2026-10-21 | Digital Banking | Change Request | Biometric login rollout checklist | High | In Progress | Ayesha Khan | 2026-10-28 |  | 2 | 2026-10-23 | 2 |  | 5 | Due Soon | Breached | 6 | 6.0098 | OK
DB-019 | 2026-10-12 | Risk | Report | Weekly suspicious activity summary | Medium | Completed | Usman Tariq | 2026-10-19 | 2026-10-19 | 5 | 2026-10-19 |  | 7 |  | Done | Met | 0 | 0.00976 | OK
DB-020 | 2026-10-22 | Finance | Report | Digital channel fee reconciliation | High | Pending | Zainab Ali | 2026-10-26 |  | 2 | 2026-10-26 | 0 |  | 4 | Due Soon | Within SLA | 6 | 6.0098 | OK
DB-021 | 2026-10-13 | Customer Support | Incident Fix | Mobile app crash complaint triage | High | Completed | Fatima Noor | 2026-10-16 | 2026-10-16 | 2 | 2026-10-15 |  | 3 |  | Done | Missed | 0 | 0.00974 | OK
DB-022 | 2026-10-14 | Marketing | Change Request | Update app store screenshots | Low | Pending | Omar Siddiqui | 2026-10-23 |  | 8 | 2026-10-26 | -3 |  | 12 | OVERDUE | Within SLA | 3 | 3.0097 | OK
DB-023 | 2026-10-08 | IT | Access Request | Test environment access for UAT team | Medium | Completed | Hamza Malik | 2026-10-13 | 2026-10-12 | 5 | 2026-10-15 |  | 4 |  | Done | Met | 0 | 0.00972 | OK
DB-024 | 2026-10-09 | Operations | Documentation | Branch operations SOP update | Low | In Progress | Sana Raza | 2026-10-20 |  | 8 | 2026-10-21 | -6 |  | 17 | OVERDUE | Breached | 3 | 3.0097 | OK
DB-025 | 2026-10-05 | Compliance | Report | Monthly AML metrics report | Medium | Completed | Bilal Ahmed | 2026-10-12 | 2026-10-12 | 5 | 2026-10-12 |  | 7 |  | Done | Met | 0 | 0.0097 | OK
DB-026 | 2026-10-06 | Digital Banking | Testing Support | Regression testing for bill payment | High | Completed | Omar Siddiqui | 2026-10-09 | 2026-10-08 | 2 | 2026-10-08 |  | 2 |  | Done | Met | 0 | 0.00969 | OK
DB-027 | 2026-10-01 | Finance | Documentation | Budget note for digital initiatives | Low | Completed | Zainab Ali | 2026-10-15 | 2026-10-14 | 8 | 2026-10-13 |  | 13 |  | Done | Missed | 0 | 0.00968 | OK
DB-028 | 2026-10-23 | Risk | Change Request | Transaction limit rule change | High | In Progress | Usman Tariq | 2026-10-28 |  | 2 | 2026-10-27 | 2 |  | 3 | Due Soon | Within SLA | 6 | 6.0097 | OK
DB-029 | 2026-10-22 | Customer Support | Documentation | Chatbot response script review | Medium | Pending | Ayesha Khan | 2026-10-30 |  | 5 | 2026-10-29 | 4 |  | 4 | On Track | Within SLA | 2 | 2.0097 | OK
DB-030 | 2026-10-07 | IT | Incident Fix | SMS gateway delay investigation | High | Completed | Hamza Malik | 2026-10-09 | 2026-10-09 | 2 | 2026-10-09 |  | 2 |  | Done | Met | 0 | 0.00965 | OK
DB-031 | 2026-10-26 | Operations | Change Request | Update cut-off time settings | Medium | Pending | Sana Raza | 2026-11-03 |  | 5 | 2026-11-02 | 8 |  | 0 | On Track | Within SLA | 2 | 2.0096 | OK
DB-032 | 2026-10-26 | Digital Banking | Testing Support | Accessibility testing for mobile app | Medium | Pending | Omar Siddiqui | 2026-11-05 |  | 5 | 2026-11-02 | 10 |  | 0 | On Track | Within SLA | 2 | 2.0096 | OK
DB-033 | 2026-10-14 | Compliance | Access Request | Auditor read-only dashboard access | Medium | Completed | Hamza Malik | 2026-10-21 | 2026-10-20 | 5 | 2026-10-21 |  | 6 |  | Done | Met | 0 | 0.00962 | OK
DB-034 | 2026-10-02 | Marketing | Report | Campaign performance snapshot | Low | Completed | Zainab Ali | 2026-10-14 | 2026-10-15 | 8 | 2026-10-14 |  | 13 |  | Done (Late) | Missed | 0 | 0.00961 | OK
DB-035 | 2026-10-16 | Finance | Compliance Review | Vendor payment control review | Medium | In Progress | Bilal Ahmed | 2026-10-27 |  | 5 | 2026-10-23 | 1 |  | 10 | Due Soon | Breached | 4 | 4.0096 | OK
DB-036 | 2026-10-23 | Risk | Access Request | Fraud tool admin access | High | Pending | Hamza Malik | 2026-10-27 |  | 2 | 2026-10-27 | 1 |  | 3 | Due Soon | Within SLA | 6 | 6.0096 | OK
DB-037 | 2026-10-21 | Customer Support | Incident Fix | Login error escalation log | Medium | In Progress | Ayesha Khan | 2026-10-28 |  | 5 | 2026-10-28 | 2 |  | 5 | Due Soon | Within SLA | 4 | 4.0096 | OK
DB-038 | 2026-10-26 | Operations | Report | Month-end digital volume report | High | Pending | Sana Raza | 2026-10-30 |  | 2 | 2026-10-28 | 4 |  | 0 | On Track | Within SLA | 3 | 3.0096 | OK
DB-039 | 2026-10-19 | Digital Banking | Documentation | Release notes for app v2.4 | Low | In Progress | Omar Siddiqui | 2026-11-02 |  | 8 | 2026-10-29 | 7 |  | 7 | On Track | Within SLA | 1 | 1.0096 | OK
DB-040 | 2026-10-01 | IT | Change Request | Server patch window schedule | Medium | Completed | Hamza Malik | 2026-10-09 | 2026-10-08 | 5 | 2026-10-08 |  | 7 |  | Done | Met | 0 | 0.00955 | OK
DB-041
DB-042
DB-043
DB-044
DB-045
DB-046
DB-047
DB-048
DB-049
DB-050
DB-051
DB-052
DB-053
DB-054
DB-055
DB-056
DB-057
DB-058
DB-059
DB-060
Formulas:
SLA Target = IF(OR([Date Raised]="",[SLA (days)]=""),"",WORKDAY([Date Raised],[SLA (days)]))

## Team
Team Roster and Capacity (fictional)
Capacity = maximum open requests a person can reasonably handle at once.
Name | Department | Capacity
Ayesha Khan | Digital Banking | 8
Hamza Malik | IT | 8
Sana Raza | Operations | 7
Bilal Ahmed | Compliance | 6
Fatima Noor | Customer Support | 7
Usman Tariq | Risk | 5
Zainab Ali | Finance | 6
Omar Siddiqui | Digital Banking | 8

## Lists
Reference Lists and Assumptions
Assumption: SLA working days and priority weights are fictional values chosen for this portfolio project.
Priority | SLA (working days) | Weight | Status | Department | Request Type
High | 2 | 3 | Pending | IT | Access Request
Medium | 5 | 2 | In Progress | Operations | Report
Low | 8 | 1 | Completed | Digital Banking | Testing Support
|  |  |  | Compliance | Incident Fix
Due Soon window (days) | 2 |  |  | Customer Support | Compliance Review
Flag logic: OVERDUE if deadline < as-of date; Due Soon if within the window above. |  |  |  | Risk | Documentation
|  |  |  | Marketing | Change Request
Finance

## How To Use
How to use this tracker
Sheets: Dashboard (summary and charts), Request Tracker (data entry), Team (roster and capacity), Lists (dropdown values and assumptions).
1. Add a new request in the next empty row of 'Request Tracker'. Fill only the yellow columns A to J; the rest calculates.
2. Use the dropdowns for Department, Request Type, Priority, Status and Assigned To. Deadline cannot be earlier than Date Raised.
3. SLA target = Date Raised plus the priority's SLA working days (Mon to Fri), set on the Lists sheet.
4. Flag: Done / Done (Late) / OVERDUE / Due Soon / On Track. SLA Status: Met / Missed for completed, Within SLA / Breached for open.
5. Risk Score = priority weight (3/2/1) x urgency (3 overdue, 2 due soon, 1 otherwise). Completed requests score 0.
6. Data Check flags rows with inconsistent dates or status; results roll up to the Dashboard (section 6).
7. To test the logic, type a date into the yellow cell C4 on the Dashboard. Clear it to return to today's date.
8. Use the filter arrows on the Request Tracker header row to sort or filter, e.g. Flag = OVERDUE or Assigned To = one person.
Colour guide on tracker rows: red = overdue, amber = due soon, green = completed.
All data is fictional and created for portfolio purposes.